AIM:

To perform Program Evaluation Review Technique (PERT) Analysis for project scheduling and

management using Python.

PROCEDURE:

1. Install Required Libraries:

o Make sure you have pandas, networkx, matplotlib, and numpy installed. You

can install them using pip if not already installed.

bash

Copy code

pip install pandas networkx matplotlib numpy

2. Define the Problem:

o Identify the tasks, their optimistic, most likely, and pessimistic durations, and

dependencies.

3. Set Up the Problem in Python:

o Use NetworkX to represent the project tasks and their dependencies.

o Calculate the expected duration and variance for each task.

o Use topological sort to identify the critical path and perform PERT analysis.

4. Run the Code:

o Execute the Python code to get the critical path, project duration, and associated

uncertainty.

5. Analyze the Output:

o Interpret the results and validate the solution against the project schedule.

CODE:
import numpy as np

import networkx as nx

import matplotlib.pyplot as plt

# Define tasks

tasks = {

'A': {'optimistic': 2, 'most_likely': 4, 'pessimistic': 6, 'dependencies': []},

'B': {'optimistic': 1, 'most_likely': 2, 'pessimistic': 3, 'dependencies': ['A']},

'C': {'optimistic': 1, 'most_likely': 3, 'pessimistic': 5, 'dependencies': ['A']},

'D': {'optimistic': 2, 'most_likely': 2, 'pessimistic': 4, 'dependencies': ['B']},

'E': {'optimistic': 3, 'most_likely': 5, 'pessimistic': 7, 'dependencies': ['C']},

'F': {'optimistic': 1, 'most_likely': 4, 'pessimistic': 6, 'dependencies': ['D', 'E']}

}

# Step 1: Calculate expected time and variance

for task, data in tasks.items():

data['duration'] = (

data['optimistic'] + 4 * data['most_likely'] + data['pessimistic']

) / 6

data['variance'] = ((data['pessimistic'] - data['optimistic']) / 6) ** 2

# Step 2: Create graph

G = nx.DiGraph()

for task, data in tasks.items():

G.add_node(task, duration=data['duration'], variance=data['variance'])

for dep in data['dependencies']:

G.add_edge(dep, task)

# Step 3: Topological order

order = list(nx.topological_sort(G))

# Step 4: Forward pass (ES, EF)

ES = {t: 0 for t in order}

EF = {}

for t in order:

EF[t] = ES[t] + G.nodes[t]['duration']

for s in G.successors(t):

ES[s] = max(ES[s], EF[t])

# Step 5: Backward pass (FIXED)

project_duration = max(EF.values())

LF = {t: project_duration for t in order}

LS = {}

for t in reversed(order):

LS[t] = LF[t] - G.nodes[t]['duration']

for p in G.predecessors(t):

LF[p] = min(LF[p], LS[t])

# Step 6: Critical Path

critical_path = [t for t in order if abs(ES[t] - LS[t]) < 1e-6]

# Step 7: Project variance & std deviation

project_variance = sum(G.nodes[t]['variance'] for t in critical_path)

project_std_dev = np.sqrt(project_variance)

# Step 8: Output

print("Earliest start times:", ES)

print("Earliest finish times:", EF)

print("Latest start times:", LS)

print("Latest finish times:", LF)

print("Critical path:", critical_path)

print("Project duration (expected):", project_duration)

print("Project standard deviation:", project_std_dev)

# Step 9: Plot graph

pos = nx.spring_layout(G)

nx.draw(G, pos, with_labels=True, node_size=3000, node_color='lightblue')

labels=nx.get_node_attributes(G,'duration')

nx.draw_networkx_edge_labels(

G, pos,

edge_labels={(u, v): f"{u}->{v}" for u, v in G.edges}

)

plt.show()

OUTPUT:

Earliest start times: {'A': 0, 'B': 4.0, 'C': 4.0, 'D': 6.0, 'E': 7.0, 'F': 12.0}

Earliest finish times: {'A': 4.0, 'B': 6.0, 'C': 7.0, 'D': 8.333333333333334, 'E': 12.0, 'F': 15.833333333333334}

Latest start times: {'F': 12.0, 'E': 7.0, 'D': 9.666666666666666, 'C': 4.0, 'B': 7.666666666666666, 'A': 0.0}

Latest finish times: {'A': 4.0, 'B': 9.666666666666666, 'C': 7.0, 'D': 12.0, 'E': 12.0, 'F': 15.833333333333334}

Critical path: ['A', 'C', 'E', 'F']

Project duration (expected): 15.833333333333334

Project standard deviation: 1.4240006242195884