AIM:

To perform Critical Path Method (CPM) Analysis for project scheduling and management using

Python.

PROCEDURE:

1. Install Required Libraries:

o Make sure you have pandas, networkx, and matplotlib installed. You can

install them using pip if not already installed.

bash

Copy code

pip install pandas networkx matplotlib

2. Define the Problem:

o Identify the tasks, their durations, and dependencies.

3. Set Up the Problem in Python:

o Use NetworkX to represent the project tasks and their dependencies.

o Use the topological sort to identify the critical path.

4. Run the Code:

o Execute the Python code to get the critical path and project duration.

5. Analyze the Output:

o Interpret the results and validate the solution against the project schedule.

CODE:

import networkx as nx

import matplotlib.pyplot as plt

tasks = {

'A': {'duration': 3, 'dependencies': []},

'B': {'duration': 2, 'dependencies': ['A']},

'C': {'duration': 4, 'dependencies': ['A']},

'D': {'duration': 2, 'dependencies': ['B']},

'E': {'duration': 3, 'dependencies': ['C']},

'F': {'duration': 1, 'dependencies': ['D', 'E']}

}

G = nx.DiGraph()

for task, data in tasks.items():

G.add_node(task, duration=data['duration'])

for dep in data['dependencies']:

G.add_edge(dep, task)

order = list(nx.topological_sort(G))

# Forward pass

ES = {t: 0 for t in order}

EF = {}

for t in order:

EF[t] = ES[t] + G.nodes[t]['duration']

for s in G.successors(t):

ES[s] = max(ES[s], EF[t])

# Backward pass (FIXED)

project_duration = max(EF.values())

LF = {t: project_duration for t in order}

LS = {}

for t in reversed(order):

LS[t] = LF[t] - G.nodes[t]['duration']

for p in G.predecessors(t):

LF[p] = min(LF[p], LS[t])

# Critical path

critical_path = [t for t in order if ES[t] == LS[t]]

print("Earliest start times:", ES)

print("Earliest finish times:", EF)

print("Latest start times:", LS)

print("Latest finish times:", LF)

print("Critical path:", critical_path)

# Plot

pos = nx.spring_layout(G)

nx.draw(G, pos, with_labels=True, node_size=3000, node_color='lightblue')

labels=nx.get_node_attributes(G,'duration')

nx.draw_networkx_edge_labels(G, pos, edge_labels={(u, v): f"{u}->{v}" for u, v in G.edges})

plt.show()

OUTPUT:

Earliest start times: {'A': 0, 'B': 3, 'C': 3, 'D': 5, 'E': 7, 'F': 10}

Earliest finish times: {'A': 3, 'B': 5, 'C': 7, 'D': 7, 'E': 10, 'F': 11}

Latest start times: {'F': 10, 'E': 7, 'D': 8, 'C': 3, 'B': 6, 'A': 0}

Latest finish times: {'A': 3, 'B': 8, 'C': 7, 'D': 10, 'E': 10, 'F': 11}

Critical path: ['A', 'C', 'E', 'F']